Self-Balancing Robot

25-Day Build Roadmap

ESP32  ·  IMU + PID balancing  ·  OLED eyes  ·  Bluetooth control

# Overview & Schedule Notes

This roadmap includes two dedicated buffer days (Day 6 and Day 15) to absorb the inevitable slippage in a hardware project like this — particularly around Days 11–14, the balancing and PID-tuning phase, which is the highest-risk and least predictable part of the build. Chassis 3D printing is started early (Day 1) and runs in the background so it isn't a bottleneck on Day 9.

If the schedule falls behind after Day 15, cut features in this order: Day 17 (wiring cleanup) first, then Day 18 (OLED personality). Both are cosmetic and can be shortened or skipped without affecting whether the robot actually balances, moves, and takes commands.

# Overall Milestones

| Days | Goal |
| --- | --- |
| 1–5 | ESP32 basics, OLED, motor control (chassis printing in background) |
| 6 | Buffer Day #1 — catch-up / chassis finishing |
| 7–9 | IMU, power, final assembly |
| 10 | PID theory (no coding) |
| 11–14 | First balance attempt → tuning → stable balance |
| 15 | Buffer Day #2 — reserved for balance overrun |
| 16 | Robustness (recovery, noise, oscillation) |
| 17–18 | Wiring cleanup + OLED personality (cut first if behind) |
| 19 | Motion while balancing |
| 20–22 | Bluetooth control + full integration |
| 23 | Polish |
| 24 | Testing + Filming |
| 25 | Edit + publish |

# Daily Plan

## Day 1 — Inventory & Planning

Goal: Know every component and get the toolchain working.

- Unbox everything and label every component.

- Find datasheets and read pinouts.

- Sketch a wiring diagram.

- Install Arduino IDE or PlatformIO.

- Install the ESP32 board package.

- Test uploading “Blink”.

- Kick off 3D printing of the first chassis part (base or legs) so it runs in the background over the next few days.

Deliverable: ESP32 successfully programmed; first print job running.

## Day 2 — Learn ESP32 Basics

Goal: Become comfortable programming the ESP32.

- GPIO output, PWM, Serial Monitor.

- Functions, variables, timing (millis()).

- Mini projects: blink LED, fade LED, print numbers.

Deliverable: Comfortable writing and uploading simple ESP32 sketches.

## Day 3 — OLED Screens

Goal: Display graphics on both OLEDs.

- Learn I2C, SDA, SCL.

- Learn the Adafruit SSD1306 library.

- Build: Hello World → static eyes → blink animation.

- Queue the next chassis part to print overnight.

Deliverable: Both OLEDs display independently.

## Day 4 — Motor Driver (Single Motor)

Goal: Spin one motor reliably.

- Learn H-bridge, PWM, and direction pins.

- Forward, backward, variable speed, stop.

Deliverable: One motor spins smoothly and predictably.

## Day 5 — Both Motors

Goal: Coordinate both motors together.

- Drive forward and backward.

- Turn left and turn right.

- Change speed on the fly.

Deliverable: Both motors behave correctly and in sync.

## Day 6 — Buffer Day #1   (Catch-up)

Goal: Absorb any slippage from Days 1–5 before moving into IMU and assembly work.

- Finish any incomplete task from Days 1–5.

- Check on / finish 3D prints; test-fit parts against motors and battery.

- Refine the wiring diagram before committing to permanent wiring.

- If on schedule instead: get ahead by starting to read BNO055 documentation.

This day has no fixed content by design — it exists to protect the rest of the schedule. Use it, don’t skip ahead just because you can.

Deliverable: Fully caught up: all Day 1–5 goals solid, chassis parts test-fitted.

## Day 7 — IMU

Goal: Understand the BNO055.

- Read pitch, roll, and yaw.

- Move the sensor around by hand and watch the values respond.

- Print values to Serial.

Deliverable: Reliable, sensible angle readings.

## Day 8 — Battery & Power

Goal: Get the full electrical system running safely.

- Wire battery → switch → buck converter → ESP32 + driver.

- Measure the 5V rail and battery voltage.

- Check current flow is sane under load.

Deliverable: Entire system powers correctly and safely.

## Day 9 — Final Chassis Assembly

Goal: Physically assemble the robot.

- All chassis parts should already be printed (from Days 1–6) — this day is assembly only, not printing.

- Mount motors, battery, ESP32, driver, and OLEDs.

Deliverable: Robot physically assembled. No balancing yet.

## Day 10 — Understand PID   (No coding)

Goal: Know WHY PID works before writing a line of tuning code.

- Understand error, P, I, D, overshoot, and oscillation.

- Watch 3Blue1Brown and Brian Douglas.

- Read worked examples.

Deliverable: Solid conceptual understanding of PID control, ready to implement it tomorrow.

## Day 11 — First PID Attempt

Goal: Get the robot attempting to stand.

- Strip the problem down to angle only.

- Forget encoders, forget Bluetooth, forget OLED logic in the loop.

- Let the robot try to balance — expect failure. That's the baseline.

Deliverable: A working (if bad) PID loop and a first sense of how the robot behaves.

## Day 12 — PID Tuning, Day 1

Goal: Begin systematic tuning.

- Adjust Kp, Kd, Ki.

- Record every attempt — numbers and short video clips (these make great future content).

Deliverable: Documented tuning log with visible improvement over Day 11.

## Day 13 — PID Tuning, Day 2

Goal: Continue tuning toward a real balance.

- Keep adjusting Kp, Kd, Ki based on Day 12's log.

- Target: robot almost balances — 2–3 seconds counts as real progress.

Deliverable: Consistent 2–3 second balance attempts.

## Day 14 — Stable Balance

Goal: 10+ seconds of continuous balancing.

- Keep tuning until the robot holds itself up reliably.

Do not move on until this works. This is the load-bearing milestone of the whole project — everything after it assumes balance is solved.

Deliverable: Robot balances for 10+ seconds.

## Day 15 — Buffer Day #2   (Reserved for balance overrun)

Goal: Protect the schedule if Day 14's target slipped.

- If Day 14's target isn't met yet: continue tuning, no new features today.

- If Day 14 succeeded: push the robot and test recovery, or get ahead on Day 16.

Deliverable: Reliable 10+ second balance, confirmed repeatable across multiple attempts.

## Day 16 — Robustness

Goal: Make the balance resilient, not just possible.

- Improve recovery behavior.

- Filter sensor noise.

- Reduce oscillation.

- Push the robot and check if/how it recovers.

Deliverable: Balance survives small disturbances, not just a static stand.

## Day 17 — Clean Wiring   (Cut first if behind schedule)

Goal: Make the build safe and camera-ready.

- Zip ties, heat shrink, cable management.

- Mount everything securely.

Skippable without affecting core function — this is the first thing to cut if the schedule is under pressure.

Deliverable: Wiring is safe, tidy, and camera-ready.

## Day 18 — OLED Eyes / Personality   (Cut second if behind schedule)

Goal: Give the robot visual character.

- Expressions: happy, blink, sleeping, surprised.

- Moving / animated eyes.

Nice-to-have, not core — the second thing to cut if the schedule is under pressure.

Deliverable: Robot has visual personality via the OLEDs.

## Day 19 — Motion While Balancing

Goal: Move the robot without it falling over.

- Add forward and backward motion.

- Add rotation.

- All while actively balancing.

Deliverable: Robot can move under balance control.

## Day 20 — Bluetooth Basics

Goal: Get phone-to-robot communication working.

- Learn ESP32 Bluetooth (Classic SPP or BLE).

- Send forward / backward / stop commands from a phone.

Deliverable: Phone can send basic commands the ESP32 receives correctly.

## Day 21 — Bluetooth UI

Goal: Build a usable control interface.

- Build phone-side buttons or a joystick control (e.g. a Bluetooth terminal app or simple custom app).

Deliverable: Usable phone control interface.

## Day 22 — Full Integration

Goal: Bring every subsystem together.

- Combine balance + motion + Bluetooth commands into one system.

Deliverable: Robot balances, moves, and responds to phone input simultaneously.

## Day 23 — Polish

Goal: Make everything reliable, not just functional once.

- Fix bugs, loose wiring, rough code, mounting issues, animation timing.

Deliverable: Everything works reliably, repeatably.

## Day 24 — Testing + Filming

Goal: Stress-test the robot and capture all raw footage.

- Test on different floors, at different battery levels, under pushes, while turning, and over a long runtime — find weaknesses.

- Film: assembly shots, failure clips, successful balance, close-ups of OLEDs, Bluetooth control in action.

Get all raw footage today so editing isn't blocked tomorrow.

Deliverable: Full raw footage library plus a known list of remaining issues.

## Day 25 — Edit & Publish

Goal: Turn footage into finished content and close out the project.

- Edit a long-form YouTube video (5–10 min) from Day 24 footage.

- Edit several short-form clips (30–60s) for TikTok/Reels.

- Write up: what you learned, biggest mistakes, what surprised you, what you'd improve next.

Tip: if you jot one line of reflection at the end of each day throughout the project (30 seconds, no extra day needed), this becomes assembly, not writing, on Day 25.

Deliverable: Published long-form video, published short-form clips, and a written reflection.